## Sheet1
Priority | User Story | Feature | Reqs | Started | Completed | Member
1 | As a File, I want to read the stats so that I can save them for the player to eventually see. | Save stats |  | 2016-04-01 | 2016-04-13
|  |  | File Write |  |  | Greg
Game Mechanics
2 | As a file, I want to provide the stats so that the player can view their stats as well as everyone who played previously. | View stats |  | 2016-04-03 | 2016-04-13
|  |  | File Read |  |  | Greg
Sorting
3 | As a player, I want to view stats so that I can compare my progress to other players. | View Stats |  | 2016-04-04 | 2016-04-14
|  |  | File Read |  |  | Greg
Sorting
4 | As a player, I want to enter my name so that my score can be contributed to a specific person. | Name entry |  | 2016-04-02 | 2016-04-14 | Lazaro
File Write
5 | As a player, I want to roll dice so that I can play the game and generate results. | Dice roll |  | 2016-04-03 | 2016-04-10 | Justin
|  |  | Number Generator |  |  | Nathan
6 | As a player, I want to build buildings so that I can get closer to beating the game, and unlock unique advantages within the game | Generate Buildings |  | 2016-04-02 | 2016-04-12 | Jeremy
|  |  | Building design |  |  | Nathan
Game mechanics
Game completion
7 | As a player, I want to pick my environment to choose which resources I start with. the game and generate results. | Choose Start |  | 2016-04-06 | 2016-04-10 | Lazaro
Name Received
8 | As a player, I want to view the help menu for instructions on how to play the game. the game and generate results. | View Info |  | 2016-04-02 | 2016-04-06 | Lazaro
|  |  | Game Started |  |  | Nathan
9 | As a player, I want to mouse over a structure to display building options giving me what resources are required to build it. the game and generate results. | View Info |  | 2016-04-05 | 2016-04-12 | Lazaro
Enviroment Chosen
10 | As a File, I want to read the stats so that I can save them for the player to eventually see. (GUI) | Save stats | UI | 2016-04-13 | 2016-04-26 | Greg
11 | As a file, I want to provide the stats so that the player can view their stats as well as everyone who played previously. | View stats | UI | 2016-04-13 | 2016-04-26 | Greg
12 | As a player, I want to view stats so that I can compare my progress to other players. | View Stats | UI | 2016-04-13 | 2016-04-26 | Greg
13 | As a player, I want to enter my name so that my score can be contributed to a specific person. | Name entry | UI | 2016-04-17 | 2016-04-24 | Jeremy
Nathan
14 | As a player, I want to roll dice so that I can play the game and generate results. | Dice roll | UI | 2016-04-22 | 2016-04-23 | Justin
15 | As a player, I want to build buildings so that I can get closer to beating the game, and unlock unique advantages within the game | Generate Buildings | UI | 2016-04-22 | 2016-04-28 | Justin
16 | As a player, I want to pick my environment to choose which resources I start with. | Choose Start | UI | 2016-04-25 | 2016-04-25 | Justin
Lazaro
17 | As a player, I want to view the help menu for instructions on how to play the game. | View Info | UI | 2016-04-24 | 2016-04-27 | Lazaro
Nathan
18 | As a player, I want to mouse over a structure to display building options giving me what resources are required to build it. | View Info | UI | 2016-04-15 | 2016-04-22 | Justin